## Executive Summary
GARMENTS ERP & CRM — SYSTEM IMPLEMENTATION TRACKER
Authoritative Cross-Stack Tracker: Frontend Next.js Screens, Workflows, APIs & Backend Monolith Engine
Project Metadata
Client / Tenant | Enterprise Garments Pvt Ltd | Country Pack | India (IN) — GST, INR (₹), FY Apr-Mar
Platform Stack | Next.js 14 App Router (Frontend) + Django Monolith REST API | Architecture Standard | Strict Monolith, Zero Direct ORM in Views
Database & Concurrency | PostgreSQL 15 (timestamptz, select_for_update) | PRD Version | v1.2 (Active Baseline)
Last Updated | 15/10/2026 | Tracker Status | Active / Release v1.1.0 Ready
Implementation Progress Telemetry
TOTAL UI SCREENS | SPECS COMPLETED | MOCKUPS READY | BACKEND APIS | TICKETS MERGED
24 | 30 | 18 | 100% | 25
Across 10 Modules | 41.7% Fully Specified | 60.0% Fully Specified | Django REST Endpoints Deployed | Production Verified
Module-Wise Screen Readiness
Module # | Module Name | Total Screens | Specs Completed | Specs Planned | Spec Readiness % | Backend API Status
Module 0 | Foundation & Multi-Tenancy | 2 | 1 | 1 | 50.0% | 100% Deployed
Module 1 | Authentication & RBAC | 2 | 1 | 1 | 50.0% | 100% Deployed
Module 2 | Master Data Governance | 3 | 0 | 3 | 0.0% | 100% Deployed
Module 3 | Procurement (Yarn Purchase Order) | 4 | 4 | 0 | 100.0% | 100% Deployed
Module 4 | Inventory & Godown Stock Ledger | 9 | 8 | 1 | 88.9% | 100% Deployed
Module 5 | Commercial Sales & Customer Returns | 5 | 4 | 1 | 80.0% | 100% Deployed
Module 6 | Knitting & Grey Fabric Production | 2 | 0 | 2 | 0.0% | 100% Deployed
Module 7 | Production Process Engine | 1 | 0 | 1 | 0.0% | 100% Deployed
Module 8 | Dual Stock & Currency Ledgers | 2 | 0 | 2 | 0.0% | 100% Deployed
Module 9 | Commercial Pricing & Job Work Valuation | 2 | 0 | 2 | 0.0% | 100% Deployed

## UI Screens Registry
ENTERPRISE UI SCREENS REGISTRY & SPECIFICATION STATUS
Comprehensive screen-by-screen tracking catalog across all ERP/CRM modules
Screen ID | Module | Screen Title / Name | Frontend Route Path | Spec Status | Spec Document File | UI Mockup Ready? | Frontend Dev Status | Backend API Status | Primary Backend REST Endpoint | PRD Ref | Target Release
SCR-AUTH-001 | Module 1: Auth | User Login & Session Scoping | /login | Complete | 01_LOGIN_UI_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | POST /api/v1/auth/login/ | §2 | v1.0.0
SCR-AUTH-002 | Module 1: Auth | Password Reset & Recovery | /forgot-password | Planned | 03_FORGOT_PASSWORD_UI_SPECIFICATION.md | Pending | Planned | Deployed | POST /api/v1/auth/password-reset/ | §2 | v1.0.0
SCR-COMP-001 | Module 0: Foundation | Company Profile, Tax & FY Setup | /administration/company | Complete | 02_COMPANY_UI_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET/PUT /api/v1/administration/companies/{id}/ | §3 | v1.0.0
SCR-DASH-001 | Module 0: Foundation | Executive & Operations Dashboard | /dashboard | Planned | 04_DASHBOARD_UI_SPECIFICATION.md | Pending | Planned | Deployed | GET /api/v1/dashboard/metrics/ | §1 | v1.0.0
SCR-MAST-001 | Module 2: Masters | Party Master (Mills, Dyers, Knitters) | /masters/parties | Planned | 05_PARTY_MASTER_UI_SPECIFICATION.md | Pending | Planned | Deployed | GET/POST /api/v1/masters/parties/ | §4.1 | v1.0.0
SCR-MAST-002 | Module 2: Masters | Yarn & Fabric Master Catalog | /masters/yarn-catalog | Planned | 06_YARN_CATALOG_UI_SPECIFICATION.md | Pending | Planned | Deployed | GET/POST /api/v1/masters/yarn-counts/ | §4.1 | v1.0.0
SCR-MAST-003 | Module 2: Masters | Godown / Warehouse Locations | /masters/godowns | Planned | 07_GODOWNS_MASTER_UI_SPECIFICATION.md | Pending | Planned | Deployed | GET/POST /api/v1/masters/warehouses/ | §4.1 | v1.0.0
SCR-PROC-001-ADD | Module 3: Procurement | Yarn Purchase Order (PO) Add Workflow | /procurement/yarn-po/new | Complete | 03_YARN_PO_ADD_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | POST /api/v1/purchase/yarn-pos/ | §4.2 | v1.0.0
SCR-PROC-001-EDIT | Module 3: Procurement | Yarn Purchase Order (PO) Edit Screen | /procurement/yarn-po/[id]/edit | Complete | 04_YARN_PO_EDIT_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | PUT/PATCH /api/v1/purchase/yarn-pos/{id}/ | §4.2 | v1.0.0
SCR-PROC-001-LIST | Module 3: Procurement | Yarn Purchase Order Register & List | /procurement/yarn-po | Complete | 05_YARN_PO_LIST_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/purchase/yarn-pos/ | §4.2 | v1.0.0
SCR-PROC-001-PRINT | Module 3: Procurement | Yarn Purchase Order Print / PDF Sheet | /procurement/yarn-po/[id]/print | Complete | 06_YARN_PO_PRINT_DOCUMENT_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/purchase/yarn-pos/{id}/ | §4.2 | v1.0.0
SCR-INVN-001-ADD | Module 4: Inventory | Yarn Inward (GRN) Add Workflow | /inventory/yarn-inward/new | Complete | 07_YARN_INWARD_ADD_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | POST /api/v1/inventory/yarn-inwards/ | §4.3 | v1.0.0
SCR-INVN-001-EDIT | Module 4: Inventory | Yarn Inward (GRN) Edit Screen | /inventory/yarn-inward/[id]/edit | Complete | 08_YARN_INWARD_EDIT_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | PUT/PATCH /api/v1/inventory/yarn-inwards/{id}/ | §4.3 | v1.0.0
SCR-INVN-001-LIST | Module 4: Inventory | Yarn Inward Register & List View | /inventory/yarn-inward | Complete | 09_YARN_INWARD_LIST_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/inventory/yarn-inwards/ | §4.3 | v1.0.0
SCR-INVN-001-PRINT | Module 4: Inventory | Yarn Inward (GRN) Print / PDF Sheet | /inventory/yarn-inward/[id]/print | Complete | 10_YARN_INWARD_PRINT_DOCUMENT_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/inventory/yarn-inwards/{id}/ | §4.3 | v1.0.0
SCR-INVN-002-ADD | Module 4: Inventory | Yarn Outward (DC) Add Workflow | /inventory/yarn-outward/new | Complete | 11_YARN_OUTWARD_ADD_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | POST /api/v1/inventory/yarn-outwards/ | §4.3 | v1.0.0
SCR-INVN-002-EDIT | Module 4: Inventory | Yarn Outward (DC) Edit Screen | /inventory/yarn-outward/[id]/edit | Complete | 12_YARN_OUTWARD_EDIT_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/inventory/yarn-stock/ | §4.3 | v1.0.0
SCR-INVN-002-LIST | Module 4: Inventory | Yarn Outward Register & List View | /inventory/yarn-outward | Complete | 13_YARN_OUTWARD_LIST_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | POST /api/v1/sales/yarn-sales/ | §4.4 | v1.1.0
SCR-INVN-002-PRINT | Module 4: Inventory | Yarn Outward (DC) Print / PDF Sheet | /inventory/yarn-outward/[id]/print | Complete | 14_YARN_OUTWARD_PRINT_DOCUMENT_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | POST /api/v1/sales/sales-returns/ | §4.4 | v1.1.0
SCR-INVN-003 | Module 4: Inventory | Live Godown Stock Register (Bags/Kg) | /inventory/stock-register | Planned | 19_STOCK_REGISTER_UI_SPECIFICATION.md | Pending | Planned | Deployed | POST /api/v1/knitting/programs/ | §4.3 | v1.1.0
SCR-SALE-001-ADD | Module 5: Commercial Sales | Yarn Sales (Invoice) Add Workflow | /sales/yarn-sales/new | Complete | 15_YARN_SALES_ADD_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/knitting/grey-fabric-stock/ | §4.3 | v1.1.0
SCR-SALE-001-EDIT | Module 5: Commercial Sales | Yarn Sales (Invoice) Edit Screen | /sales/yarn-sales/[id]/edit | Complete | 16_YARN_SALES_EDIT_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET /api/v1/ledger/party-ledger/ | §4.6 | v1.1.0
SCR-SALE-001-LIST | Module 5: Commercial Sales | Yarn Sales Register & List View | /sales/yarn-sales | Complete | 17_YARN_SALES_LIST_WORKFLOW_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET/POST /api/v1/pricing/price-lists/ | §4.5 | v1.2.0
SCR-SALE-001-PRINT | Module 5: Commercial Sales | Yarn Sales Tax Invoice Print / PDF | /sales/yarn-sales/[id]/print | Complete | 18_YARN_SALES_PRINT_DOCUMENT_SPECIFICATION.md | Yes (Sample JPG) | Ready for Dev | Deployed | GET/POST /api/v1/pricing/job-rules/ | §4.5 | v1.2.0
SCR-SALE-002 | Module 5: Commercial Sales | Customer Sales Return & Re-crediting | /sales/returns | Planned | 20_SALES_RETURN_UI_SPECIFICATION.md | Pending | Planned | Deployed
SCR-KNIT-001 | Module 6: Knitting | Knitting Program Job Card Planning | /production/knitting-program | Planned | 21_KNITTING_PROGRAM_UI_SPECIFICATION.md | Pending | Planned | Deployed
SCR-KNIT-002 | Module 6: Knitting | Grey Fabric Inward & Outward Register | /production/grey-fabric | Planned | 22_GREY_FABRIC_UI_SPECIFICATION.md | Pending | Planned | Deployed
SCR-FINL-001 | Module 8: Ledgers | Party Financial Ledger & Reconciliation | /ledgers/party-ledger | Planned | 23_PARTY_LEDGER_UI_SPECIFICATION.md | Pending | Planned | Deployed
SCR-PRIC-001 | Module 9: Pricing Engine | Multi-Tier Price Lists & Slabs | /pricing/price-lists | Planned | 24_PRICE_LISTS_UI_SPECIFICATION.md | Pending | Planned | Deployed
SCR-PRIC-002 | Module 9: Pricing Engine | Job Work Subcontract Conversion Matrix | /pricing/job-work-rules | Planned | 25_JOB_WORK_MATRIX_UI_SPECIFICATION.md | Pending | Planned | Deployed

## Backend Tickets
BACKEND MONOLITH TICKETS & API INVARIANTS
Tracked backend engineering tasks and database models from docs/TRACKER.md
Ticket ID | Mod # | Title / Technical Scope | PRD Ref | Status | Owner Team | Branch / PR | E2E Verified | Reviewer | Release | AI Usage | Key Models & Services
T9-001 | 9 | Unified Price Lists (Purchase, Sales, Job Work, Party & General) | §4.5 | Merged | Pricing Team | main | Yes | Lead | v1.2.0 | High | tm_price_list, tm_price_list_item, tm_price_list_job_rule, ta_pricing_audit
T9-002 | 9 | Job Work Subcontract Conversion Rate Engine & Multi-Tier Resolution API | §4.5 | In review | Pricing Team | feature/T9-002-engine | Yes | Lead | v1.2.0 | High | /api/v1/pricing/resolve/ (Yarn & Job Work), job-rules CRUD, 13 automated tests passed
T0-001 | 0 | Workspace, base models, standard JSON envelope | §1 | Merged | Core Team | main | Yes | Lead | v1.0.0 | High | TimeStamped, SoftDelete, Uppercase
T0-002 | 0 | Tenant & Financial Year Middleware | §3 | Merged | Core Team | main | Yes | Lead | v1.0.0 | High | TenantMiddleware, X-Company-ID
T1-001 | 1 | Custom User, Role, Privilege, SimpleJWT Auth | §2 | Merged | Auth Team | main | Yes | Lead | v1.0.0 | High | 18 permission modules
T1-002 | 1 | Dual-route aliases and CORS header support | §2 | Merged | Auth Team | main | Yes | Lead | v1.0.0 | High | /api/v1/auth/login direct route
T2-001 | 2 | Textile Masters (Parties, Yarn, Fabric, Process, Godowns) | §4.1 | Merged | Masters Team | main | Yes | Lead | v1.0.0 | High | UOM, Counts, Colors, Fabrics
T2-002 | 2 | Quality Program carton nested sizing | §4.1 | Merged | Masters Team | main | Yes | Lead | v1.0.0 | High | Box ratios, nested serializers
T2-003 | 2 | Tax Master & GST Engine (0%, 5%, 12%, 18%, 28%, HSN/SAC) | §4.1 | Merged | Masters Team | main | Yes | Lead | v1.1.0 | High | mx_tax, TaxEngine, seed_defaults
T3-001 | 3 | Yarn Purchase Orders with split delivery schedules | §4.2 | Merged | PO Team | main | Yes | Lead | v1.0.0 | High | Draft, auto FY resolution
T3-002 | 3 | PO Authorization locking and soft-delete safeguards | §4.2 | Merged | PO Team | main | Yes | Lead | v1.0.0 | High | Prevents delete of active POs
T3-003 | 3 | Yarn PO live balance database view scoping | §4.2 | Merged | PO Team | main | Yes | Lead | v1.0.0 | High | Scoped to active company POs
T3-004 | 3 | Company-Configurable Multi-Type Yarn POs (Melange, Blended, Wound) | §4.2 | Merged | PO Team | main | Yes | Lead | v1.1.0 | High | tc_company_yarn_type, dynamic conditional validation
T4-001 | 4 | Live Godown Stock Ledger (Bags & Weight tracking) | §4.3 | Merged | Inv Team | main | Yes | Lead | v1.0.0 | High | tm_yarn_stock atomic locks
T4-002 | 4 | Inward GRN with Multi-Type Yarn Specs, GST Tax & PO deduction | §4.3 | Merged | Inv Team | main | Yes | Lead | v1.1.0 | High | child_yarn_inward_table, technical specs, TaxEngine
T4-003 | 4 | Delivery Challan Outward with bag non-negative check | §4.3 | Merged | Inv Team | main | Yes | Lead | v1.0.0 | High | Prevents bag underflow
T4-004 | 4 | Atomic cancellation and stock rollback | §4.3 | Merged | Inv Team | main | Yes | Lead | v1.0.0 | High | cancel_inward, cancel_outward
T5-001 | 5 | Commercial Sales Tax Invoices & Stock Deductions | §4.4 | Merged | Sales Team | main | Yes | Lead | v1.1.0 | High | GST taxes (CGST/SGST/IGST), child_yarn_sales
T5-002 | 5 | Customer Sales Returns with GST Tax & Stock Re-crediting | §4.4 | Merged | Sales Team | main | Yes | Lead | v1.1.0 | High | Re-credits physical stock, GST TaxEngine
T5-003 | 5 | Sales and Sales Return atomic cancellation workflows | §4.4 | Merged | Sales Team | main | Yes | Lead | v1.0.0 | High | cancel_sales, cancel_sales_return
T6-001 | 6 | Knitting Program (Job Card) planning & requirement engine | §4.3 | Merged | Knitting Team | main | Yes | Lead | v1.1.0 | High | tm_knitting_program, loss %
T6-002 | 6 | Live Grey Fabric Stock Ledger (Rolls & Kg tracking) | §4.3 | Merged | Knitting Team | main | Yes | Lead | v1.1.0 | High | tm_grey_fabric_stock locks
T6-003 | 6 | Grey Fabric Inward GRN with process loss & job charges | §4.3 | Merged | Knitting Team | main | Yes | Lead | v1.1.0 | High | tm_grey_fabric_inward
T6-004 | 6 | Grey Fabric Outward DC for Dyeing & Knitter Return | §4.3 | Merged | Knitting Team | main | Yes | Lead | v1.1.0 | High | tm_grey_fabric_outward
T8-001 | 8 | Dual Stock & Currency Ledger Engine (In/Out, Dr/Cr) | §4.6 | Merged | Ledger Team | main | Yes | Lead | v1.1.0 | High | tl_stock_movement, tm_stage_stock, tl_voucher, tl_voucher_line
T8-002 | 8 | Party Financial Ledger Maintenance & Payment Workflows | §4.6 | Merged | Ledger Team | main | Yes | Lead | v1.1.0 | High | Opening balance, date range filter, payment/receipt recording

## Procurement & Inward Flow
END-TO-END YARN WORKFLOW & LEDGER TRACEABILITY MATRIX
Audit trail from Yarn PO creation through weighbridge inward GRN to double-entry ledger
Step # | Lifecycle Stage | Screen ID | Frontend Route | Source Document | Destination Table | Stock Effect (tm_yarn_stock) | Financial Ledger Effect | PO Balance Effect | Status
1 | Purchase Order Creation | SCR-PROC-001-ADD | /procurement/yarn-po/new | Commercial PO Draft | tm_yarn_po, tx_yarn_po | None (Pending Order) | None | Creates Expected PO Balance | Fully Specified
2 | PO Approval & Locking | SCR-PROC-001-ADD/EDIT | /procurement/yarn-po/[id]/edit | Approved PO | tm_yarn_po (is_authorized=1) | Locks PO against edits | None | Activates Pending Balance for Inward | Fully Specified
3 | PO Print & Vendor Issue | SCR-PROC-001-PRINT | /procurement/yarn-po/[id]/print | Vendor PO Copy (A4) | N/A (Document Print) | None | None | None | Fully Specified
4 | Gate Entry (Security) | SCR-INVN-001-ADD | /inventory/yarn-inward/new | Supplier DC / Lorry Pass | tm_yarn_inward (is_authorized=0) | None (Gate Draft) | None | None (Unposted) | Fully Specified
5 | Weighbridge Measurement | SCR-INVN-001-ADD | /inventory/yarn-inward/new | Gross & Tare Scale Read | tx_yarn_inward (Weighbridge rows) | None | None | None | Fully Specified
6 | GRN Post & Stock Ledger | SCR-INVN-001-ADD | /inventory/yarn-inward/new | Authorized GRN | tm_yarn_stock | +inward_bag, +inward_qty (Atomic Lock) | CurrencyLedgerService Voucher | Deducts remaining_bag/qty (Completes PO) | Fully Specified
7 | GRN Commercial Sign-Off | SCR-INVN-001-PRINT | /inventory/yarn-inward/[id]/print | 4-Tier Signed GRN (A4) | N/A (Document Print) | None | Accounts Payable 3-Way Match | None | Fully Specified
8 | Downstream Consumption | SCR-INVN-001-EDIT | /inventory/yarn-inward/[id]/edit | Outward DC / Sales | tm_yarn_stock | Deducts stock for Knitting/Dyeing | Outward Voucher | Blocks Inward Cancellation if consumed | Fully Specified
9 | Atomic Rollback / Reversal | SCR-INVN-001-EDIT | /inventory/yarn-inward/[id]/edit | Cancelled Inward GRN | tm_yarn_stock (Rollback) | Reverses inward_bag & inward_qty | Contra Reversal Voucher | Restores remaining_bag/qty to PO | Fully Specified
10 | Outward DC Creation (Knitting/Dyeing/Return) | SCR-INVN-002-ADD | /inventory/yarn-outward/new | Delivery Challan Draft | tm_yarn_outward, tx_yarn_outward | -outward_bag, -outward_qty (Atomic Lock)
11 | Outward DC Print & E-Way Bill Pass | SCR-INVN-002-PRINT | /inventory/yarn-outward/[id]/print | GST Rule 55 DC Copy (A4) | N/A (Document Print) | None
12 | Outward DC Register & Processor Balances | SCR-INVN-002-LIST | /inventory/yarn-outward | Outward Register | tm_yarn_outward | Tracks remaining_quantity at processor
13 | Atomic DC Reversal / Cancellation | SCR-INVN-002-EDIT | /inventory/yarn-outward/[id]/edit | Cancelled Outward DC | tm_yarn_stock (Reversal) | Restores balance_bag & balance_qty
14 | Commercial Sales Invoice Creation | SCR-SALE-001-ADD | /sales/yarn-sales/new | Sales Tax Invoice Draft | tm_yarn_sales, tx_yarn_sales | -sales_bag, -sales_qty (Atomic Lock)
15 | GST Tax Invoice Print & Dispatch | SCR-SALE-001-PRINT | /sales/yarn-sales/[id]/print | Statutory Rule 46 Tax Invoice (A4) | N/A (Document Print) | None
16 | Sales Register & Output Tax Audit | SCR-SALE-001-LIST | /sales/yarn-sales | Commercial Sales Register | tm_yarn_sales | Tracks billed turnover & GST output liability
17 | Sales Return Dependency & Invoice Reversal | SCR-SALE-001-EDIT | /sales/yarn-sales/[id]/edit | Cancelled Sales Invoice | tm_yarn_stock (Reversal) | Restores stock if returns == 0