## Executive Summary
GARMENTS ERP & CRM — SYSTEM IMPLEMENTATION TRACKER
Authoritative Cross-Stack Telemetry: Frontend Next.js Screens, Workflows, APIs & Backend Engine
PROJECT METADATA
Client / Tenant | Enterprise Garments Pvt Ltd |  |  | Country Pack | India (IN) — GST, INR (₹), FY Apr-Mar
Platform Stack | Next.js 14 App Router (Frontend) + Django Monolith REST API |  |  | Architecture Standard | Strict Monolith, Zero Direct ORM in Views
Database & Concurrency | PostgreSQL 15 (timestamptz, select_for_update) |  |  | PRD Reference | PRD v1.2 Baseline
Last Synchronized | 16/10/2026 |  |  | Tracker Status | Active / Release v1.1.0 Ready
OVERALL SPECIFICATION & DEVELOPMENT TELEMETRY
TOTAL SCREENS | SPECS COMPLETED | COMPLETION % | SPECS PLANNED | BACKEND APIS | MOCKUPS READY | STATUS
39 | 39 | 100.0% | 0 | 100% Deployed | 7 Generated | ON TRACK
STAGE-BY-STAGE / WORKFLOW SUITE SPECIFICATION PROGRESS
Stage / Workflow Suite | Module Ref | Total Screens | Complete | Planned | Progress % | Readiness Status
Authentication & Session | Mod 1 | 2 | 2 | 0 | 100.0% | READY FOR DEV
Foundation & Multi-Tenancy | Mod 0 | 2 | 2 | 0 | 100.0% | READY FOR DEV
Master Data Governance | Mod 2 | 3 | 3 | 0 | 100.0% | READY FOR DEV
Yarn Purchase Order (PO) | Mod 3 | 4 | 4 | 0 | 100.0% | READY FOR DEV
Yarn Inward (GRN) | Mod 4 | 4 | 4 | 0 | 100.0% | READY FOR DEV
Yarn Outward (DC) | Mod 4 | 4 | 4 | 0 | 100.0% | READY FOR DEV
Live Godown Stock Ledger | Mod 4 | 1 | 1 | 0 | 100.0% | READY FOR DEV
Party Stock Ledger & Job Work | Mod 4 | 1 | 1 | 0 | 100.0% | READY FOR DEV
Commercial Yarn Sales (Invoice) | Mod 5 | 4 | 4 | 0 | 100.0% | READY FOR DEV
Customer Yarn Sales Return | Mod 5 | 4 | 4 | 0 | 100.0% | READY FOR DEV
Knitting & Fabric Production | Mod 6 | 2 | 2 | 0 | 100.0% | READY FOR DEV
Yarn Price Lists | Mod 9 | 4 | 4 | 0 | 100.0% | READY FOR DEV
Job Work Subcontract Matrix | Mod 9 | 1 | 1 | 0 | 100.0% | READY FOR DEV
Production Process Engine | Mod 7 | 1 | 1 | 0 | 100.0% | READY FOR DEV
Financial Ledgers & Accounting | Mod 8 | 2 | 2 | 0 | 100.0% | READY FOR DEV

## Stage & Workflow Suites
TRANSACTIONAL 4-SCREEN SUITES & SPECIALIZED REGISTERS
Stage / Workflow Suite | Screen ID | Screen Role (Add/Edit/List/Print) | Screen Title | Route Path | Spec Status | Spec Document | PRD Ref
Authentication & Session | SCR-AUTH-001 | Analytical Register | User Login & Session Scoping | /login | Complete | 01_LOGIN_UI_SPECIFICATION.md | §2
Authentication & Session | SCR-AUTH-002 | Analytical Register | Password Reset & Credential Recovery | /forgot-password | Complete | 39_FORGOT_PASSWORD_UI_SPECIFICATION.md | §2
Foundation & Multi-Tenancy | SCR-COMP-001 | Analytical Register | Company Profile, Tax & FY Setup | /administration/company | Complete | 02_COMPANY_UI_SPECIFICATION.md | §3
Foundation & Multi-Tenancy | SCR-DASH-001 | Analytical Register | Executive & Operations Dashboard | /dashboard | Complete | 38_DASHBOARD_UI_SPECIFICATION.md | §1
Master Data Governance | SCR-MAST-001 | Analytical Register | Party Master (Mills, Dyers, Knitters) | /masters/parties | Complete | 29_PARTY_MASTER_UI_SPECIFICATION.md | §4.1
Master Data Governance | SCR-MAST-002 | Analytical Register | Yarn & Fabric Master Catalog | /masters/yarn-catalog | Complete | 30_YARN_CATALOG_UI_SPECIFICATION.md | §4.1
Master Data Governance | SCR-MAST-003 | Analytical Register | Godown / Warehouse Locations Master | /masters/godowns | Complete | 31_GODOWNS_MASTER_UI_SPECIFICATION.md | §4.1
Yarn Purchase Order (PO) | SCR-PROC-001-ADD | 1. Add Workflow | Yarn Purchase Order (PO) Add Workflow | /procurement/yarn-po/new | Complete | 03_YARN_PO_ADD_WORKFLOW_SPECIFICATION.md | §4.2
Yarn Purchase Order (PO) | SCR-PROC-001-EDIT | 2. Edit Screen | Yarn Purchase Order (PO) Edit Screen | /procurement/yarn-po/[id]/edit | Complete | 04_YARN_PO_EDIT_WORKFLOW_SPECIFICATION.md | §4.2
Yarn Purchase Order (PO) | SCR-PROC-001-LIST | 3. Register List | Yarn Purchase Order Register & List | /procurement/yarn-po | Complete | 05_YARN_PO_LIST_WORKFLOW_SPECIFICATION.md | §4.2
Yarn Purchase Order (PO) | SCR-PROC-001-PRINT | 4. Print Document | Yarn Purchase Order Print / PDF Sheet | /procurement/yarn-po/[id]/print | Complete | 06_YARN_PO_PRINT_DOCUMENT_SPECIFICATION.md | §4.2
Yarn Inward (GRN) | SCR-INVN-001-ADD | 1. Add Workflow | Yarn Inward (GRN) Add Workflow | /inventory/yarn-inward/new | Complete | 07_YARN_INWARD_ADD_WORKFLOW_SPECIFICATION.md | §4.3
Yarn Inward (GRN) | SCR-INVN-001-EDIT | 2. Edit Screen | Yarn Inward (GRN) Edit Screen | /inventory/yarn-inward/[id]/edit | Complete | 08_YARN_INWARD_EDIT_WORKFLOW_SPECIFICATION.md | §4.3
Yarn Inward (GRN) | SCR-INVN-001-LIST | 3. Register List | Yarn Inward Register & List View | /inventory/yarn-inward | Complete | 09_YARN_INWARD_LIST_WORKFLOW_SPECIFICATION.md | §4.3
Yarn Inward (GRN) | SCR-INVN-001-PRINT | 4. Print Document | Yarn Inward (GRN) Print / PDF Sheet | /inventory/yarn-inward/[id]/print | Complete | 10_YARN_INWARD_PRINT_DOCUMENT_SPECIFICATION.md | §4.3
Yarn Outward (DC) | SCR-INVN-002-ADD | 1. Add Workflow | Yarn Outward (DC) Add Workflow | /inventory/yarn-outward/new | Complete | 11_YARN_OUTWARD_ADD_WORKFLOW_SPECIFICATION.md | §4.3
Yarn Outward (DC) | SCR-INVN-002-EDIT | 2. Edit Screen | Yarn Outward (DC) Edit Screen | /inventory/yarn-outward/[id]/edit | Complete | 12_YARN_OUTWARD_EDIT_WORKFLOW_SPECIFICATION.md | §4.3
Yarn Outward (DC) | SCR-INVN-002-LIST | 3. Register List | Yarn Outward Register & List View | /inventory/yarn-outward | Complete | 13_YARN_OUTWARD_LIST_WORKFLOW_SPECIFICATION.md | §4.3
Yarn Outward (DC) | SCR-INVN-002-PRINT | 4. Print Document | Yarn Outward (DC) Print / PDF Sheet | /inventory/yarn-outward/[id]/print | Complete | 14_YARN_OUTWARD_PRINT_DOCUMENT_SPECIFICATION.md | §4.3
Live Godown Stock Ledger | SCR-INVN-003 | Analytical Register | Live Godown Stock Ledger & Register | /inventory/stock-ledger | Complete | 27_STOCK_LEDGER_UI_SPECIFICATION.md | §4.3
Party Stock Ledger & Job Work | SCR-INVN-004 | Analytical Register | Party Stock Ledger & Job Work Reconciliation | /inventory/party-stock-ledger | Complete | 28_PARTY_STOCK_LEDGER_UI_SPECIFICATION.md | §4.3, §4.6
Commercial Yarn Sales (Invoice) | SCR-SALE-001-ADD | 1. Add Workflow | Yarn Sales (Invoice) Add Workflow | /sales/yarn-sales/new | Complete | 15_YARN_SALES_ADD_WORKFLOW_SPECIFICATION.md | §4.4
Commercial Yarn Sales (Invoice) | SCR-SALE-001-EDIT | 2. Edit Screen | Yarn Sales (Invoice) Edit Screen | /sales/yarn-sales/[id]/edit | Complete | 16_YARN_SALES_EDIT_WORKFLOW_SPECIFICATION.md | §4.4
Commercial Yarn Sales (Invoice) | SCR-SALE-001-LIST | 3. Register List | Yarn Sales Register & List View | /sales/yarn-sales | Complete | 17_YARN_SALES_LIST_WORKFLOW_SPECIFICATION.md | §4.4
Commercial Yarn Sales (Invoice) | SCR-SALE-001-PRINT | 4. Print Document | Yarn Sales Tax Invoice Print / PDF | /sales/yarn-sales/[id]/print | Complete | 18_YARN_SALES_PRINT_DOCUMENT_SPECIFICATION.md | §4.4
Customer Yarn Sales Return | SCR-SALE-002-ADD | 1. Add Workflow | Yarn Sales Return Add Workflow | /sales/yarn-sales-returns/new | Complete | 19_YARN_SALES_RETURN_ADD_WORKFLOW_SPECIFICATION.md | §4.4
Customer Yarn Sales Return | SCR-SALE-002-EDIT | 2. Edit Screen | Yarn Sales Return Edit Screen | /sales/yarn-sales-returns/[id]/edit | Complete | 20_YARN_SALES_RETURN_EDIT_WORKFLOW_SPECIFICATION.md | §4.4
Customer Yarn Sales Return | SCR-SALE-002-LIST | 3. Register List | Yarn Sales Return List & Register | /sales/yarn-sales-returns | Complete | 21_YARN_SALES_RETURN_LIST_WORKFLOW_SPECIFICATION.md | §4.4
Customer Yarn Sales Return | SCR-SALE-002-PRINT | 4. Print Document | Yarn Sales Return (Credit Note) Print | /sales/yarn-sales-returns/[id]/print | Complete | 22_YARN_SALES_RETURN_PRINT_DOCUMENT_SPECIFICATION.md | §4.4
Knitting & Fabric Production | SCR-KNIT-001 | Analytical Register | Knitting Program Job Card Planning | /production/knitting-program | Complete | 32_KNITTING_PROGRAM_UI_SPECIFICATION.md | §4.3
Knitting & Fabric Production | SCR-KNIT-002 | Analytical Register | Grey Fabric Inward, Outward & Live Stock | /production/grey-fabric | Complete | 33_GREY_FABRIC_UI_SPECIFICATION.md | §4.3
Yarn Price Lists | SCR-PRIC-001-ADD | 1. Add Workflow | Yarn Price List Add Workflow | /pricing/yarn-price-lists/new | Complete | 23_YARN_PRICE_LIST_ADD_WORKFLOW_SPECIFICATION.md | §4.5
Yarn Price Lists | SCR-PRIC-001-EDIT | 2. Edit Screen | Yarn Price List Edit & Revision | /pricing/yarn-price-lists/[id]/edit | Complete | 24_YARN_PRICE_LIST_EDIT_WORKFLOW_SPECIFICATION.md | §4.5
Yarn Price Lists | SCR-PRIC-001-LIST | 3. Register List | Yarn Price List Register & Management | /pricing/yarn-price-lists | Complete | 25_YARN_PRICE_LIST_LIST_WORKFLOW_SPECIFICATION.md | §4.5
Yarn Price Lists | SCR-PRIC-001-PRINT | 4. Print Document | Yarn Price List (Rate Card) Print | /pricing/yarn-price-lists/[id]/print | Complete | 26_YARN_PRICE_LIST_PRINT_DOCUMENT_SPECIFICATION.md | §4.5
Job Work Subcontract Matrix | SCR-PRIC-002 | Analytical Register | Job Work Subcontract Conversion Matrix | /pricing/job-work-rules | Complete | 37_JOB_WORK_MATRIX_UI_SPECIFICATION.md | §4.5
Production Process Engine | SCR-PRCS-001 | Analytical Register | Production Process Routing & Tracking | /production/process-routing | Complete | 34_PROCESS_ROUTING_UI_SPECIFICATION.md | §4.5
Financial Ledgers & Accounting | SCR-FINL-001 | Analytical Register | Party Financial Ledger & Reconciliation | /ledgers/party-ledger | Complete | 35_PARTY_FINANCIAL_LEDGER_UI_SPECIFICATION.md | §4.6
Financial Ledgers & Accounting | SCR-FINL-002 | Analytical Register | General Ledger & Multi-Period Trial Balance | /ledgers/trial-balance | Complete | 36_TRIAL_BALANCE_UI_SPECIFICATION.md | §4.6

## UI Screens Registry
ENTERPRISE UI SCREENS REGISTRY & SPECIFICATION STATUS
Screen ID | Module | Stage / Workflow Suite | Screen Title / Name | Frontend Route Path | Spec Status | UI Mockup | API Status | Specification File
SCR-AUTH-001 | Mod 1 | Authentication & Session | User Login & Session Scoping | /login | Complete | 🎨 Mockup Ready | ✅ Deployed | 01_LOGIN_UI_SPECIFICATION.md
SCR-AUTH-002 | Mod 1 | Authentication & Session | Password Reset & Credential Recovery | /forgot-password | Complete | 🎨 Mockup Ready | ✅ Deployed | 39_FORGOT_PASSWORD_UI_SPECIFICATION.md
SCR-COMP-001 | Mod 0 | Foundation & Multi-Tenancy | Company Profile, Tax & FY Setup | /administration/company | Complete | 🎨 Mockup Ready | ✅ Deployed | 02_COMPANY_UI_SPECIFICATION.md
SCR-DASH-001 | Mod 0 | Foundation & Multi-Tenancy | Executive & Operations Dashboard | /dashboard | Complete | 🎨 Mockup Ready | ✅ Deployed | 38_DASHBOARD_UI_SPECIFICATION.md
SCR-MAST-001 | Mod 2 | Master Data Governance | Party Master (Mills, Dyers, Knitters) | /masters/parties | Complete | 🎨 Mockup Ready | ✅ Deployed | 29_PARTY_MASTER_UI_SPECIFICATION.md
SCR-MAST-002 | Mod 2 | Master Data Governance | Yarn & Fabric Master Catalog | /masters/yarn-catalog | Complete | 🎨 Mockup Ready | ✅ Deployed | 30_YARN_CATALOG_UI_SPECIFICATION.md
SCR-MAST-003 | Mod 2 | Master Data Governance | Godown / Warehouse Locations Master | /masters/godowns | Complete | 🎨 Mockup Ready | ✅ Deployed | 31_GODOWNS_MASTER_UI_SPECIFICATION.md
SCR-PROC-001-ADD | Mod 3 | Yarn Purchase Order (PO) | Yarn Purchase Order (PO) Add Workflow | /procurement/yarn-po/new | Complete | 🎨 Mockup Ready | ✅ Deployed | 03_YARN_PO_ADD_WORKFLOW_SPECIFICATION.md
SCR-PROC-001-EDIT | Mod 3 | Yarn Purchase Order (PO) | Yarn Purchase Order (PO) Edit Screen | /procurement/yarn-po/[id]/edit | Complete | 🎨 Mockup Ready | ✅ Deployed | 04_YARN_PO_EDIT_WORKFLOW_SPECIFICATION.md
SCR-PROC-001-LIST | Mod 3 | Yarn Purchase Order (PO) | Yarn Purchase Order Register & List | /procurement/yarn-po | Complete | 🎨 Mockup Ready | ✅ Deployed | 05_YARN_PO_LIST_WORKFLOW_SPECIFICATION.md
SCR-PROC-001-PRINT | Mod 3 | Yarn Purchase Order (PO) | Yarn Purchase Order Print / PDF Sheet | /procurement/yarn-po/[id]/print | Complete | 🎨 Mockup Ready | ✅ Deployed | 06_YARN_PO_PRINT_DOCUMENT_SPECIFICATION.md
SCR-INVN-001-ADD | Mod 4 | Yarn Inward (GRN) | Yarn Inward (GRN) Add Workflow | /inventory/yarn-inward/new | Complete | 🎨 Mockup Ready | ✅ Deployed | 07_YARN_INWARD_ADD_WORKFLOW_SPECIFICATION.md
SCR-INVN-001-EDIT | Mod 4 | Yarn Inward (GRN) | Yarn Inward (GRN) Edit Screen | /inventory/yarn-inward/[id]/edit | Complete | 🎨 Mockup Ready | ✅ Deployed | 08_YARN_INWARD_EDIT_WORKFLOW_SPECIFICATION.md
SCR-INVN-001-LIST | Mod 4 | Yarn Inward (GRN) | Yarn Inward Register & List View | /inventory/yarn-inward | Complete | 🎨 Mockup Ready | ✅ Deployed | 09_YARN_INWARD_LIST_WORKFLOW_SPECIFICATION.md
SCR-INVN-001-PRINT | Mod 4 | Yarn Inward (GRN) | Yarn Inward (GRN) Print / PDF Sheet | /inventory/yarn-inward/[id]/print | Complete | 🎨 Mockup Ready | ✅ Deployed | 10_YARN_INWARD_PRINT_DOCUMENT_SPECIFICATION.md
SCR-INVN-002-ADD | Mod 4 | Yarn Outward (DC) | Yarn Outward (DC) Add Workflow | /inventory/yarn-outward/new | Complete | 🎨 Mockup Ready | ✅ Deployed | 11_YARN_OUTWARD_ADD_WORKFLOW_SPECIFICATION.md
SCR-INVN-002-EDIT | Mod 4 | Yarn Outward (DC) | Yarn Outward (DC) Edit Screen | /inventory/yarn-outward/[id]/edit | Complete | 🎨 Mockup Ready | ✅ Deployed | 12_YARN_OUTWARD_EDIT_WORKFLOW_SPECIFICATION.md
SCR-INVN-002-LIST | Mod 4 | Yarn Outward (DC) | Yarn Outward Register & List View | /inventory/yarn-outward | Complete | 🎨 Mockup Ready | ✅ Deployed | 13_YARN_OUTWARD_LIST_WORKFLOW_SPECIFICATION.md
SCR-INVN-002-PRINT | Mod 4 | Yarn Outward (DC) | Yarn Outward (DC) Print / PDF Sheet | /inventory/yarn-outward/[id]/print | Complete | 🎨 Mockup Ready | ✅ Deployed | 14_YARN_OUTWARD_PRINT_DOCUMENT_SPECIFICATION.md
SCR-INVN-003 | Mod 4 | Live Godown Stock Ledger | Live Godown Stock Ledger & Register | /inventory/stock-ledger | Complete | 🎨 Mockup Ready | ✅ Deployed | 27_STOCK_LEDGER_UI_SPECIFICATION.md
SCR-INVN-004 | Mod 4 | Party Stock Ledger & Job Work | Party Stock Ledger & Job Work Reconciliation | /inventory/party-stock-ledger | Complete | 🎨 Mockup Ready | ✅ Deployed | 28_PARTY_STOCK_LEDGER_UI_SPECIFICATION.md
SCR-SALE-001-ADD | Mod 5 | Commercial Yarn Sales (Invoice) | Yarn Sales (Invoice) Add Workflow | /sales/yarn-sales/new | Complete | 🎨 Mockup Ready | ✅ Deployed | 15_YARN_SALES_ADD_WORKFLOW_SPECIFICATION.md
SCR-SALE-001-EDIT | Mod 5 | Commercial Yarn Sales (Invoice) | Yarn Sales (Invoice) Edit Screen | /sales/yarn-sales/[id]/edit | Complete | 🎨 Mockup Ready | ✅ Deployed | 16_YARN_SALES_EDIT_WORKFLOW_SPECIFICATION.md
SCR-SALE-001-LIST | Mod 5 | Commercial Yarn Sales (Invoice) | Yarn Sales Register & List View | /sales/yarn-sales | Complete | 🎨 Mockup Ready | ✅ Deployed | 17_YARN_SALES_LIST_WORKFLOW_SPECIFICATION.md
SCR-SALE-001-PRINT | Mod 5 | Commercial Yarn Sales (Invoice) | Yarn Sales Tax Invoice Print / PDF | /sales/yarn-sales/[id]/print | Complete | 🎨 Mockup Ready | ✅ Deployed | 18_YARN_SALES_PRINT_DOCUMENT_SPECIFICATION.md
SCR-SALE-002-ADD | Mod 5 | Customer Yarn Sales Return | Yarn Sales Return Add Workflow | /sales/yarn-sales-returns/new | Complete | 🎨 Mockup Ready | ✅ Deployed | 19_YARN_SALES_RETURN_ADD_WORKFLOW_SPECIFICATION.md
SCR-SALE-002-EDIT | Mod 5 | Customer Yarn Sales Return | Yarn Sales Return Edit Screen | /sales/yarn-sales-returns/[id]/edit | Complete | 🎨 Mockup Ready | ✅ Deployed | 20_YARN_SALES_RETURN_EDIT_WORKFLOW_SPECIFICATION.md
SCR-SALE-002-LIST | Mod 5 | Customer Yarn Sales Return | Yarn Sales Return List & Register | /sales/yarn-sales-returns | Complete | 🎨 Mockup Ready | ✅ Deployed | 21_YARN_SALES_RETURN_LIST_WORKFLOW_SPECIFICATION.md
SCR-SALE-002-PRINT | Mod 5 | Customer Yarn Sales Return | Yarn Sales Return (Credit Note) Print | /sales/yarn-sales-returns/[id]/print | Complete | 🎨 Mockup Ready | ✅ Deployed | 22_YARN_SALES_RETURN_PRINT_DOCUMENT_SPECIFICATION.md
SCR-KNIT-001 | Mod 6 | Knitting & Fabric Production | Knitting Program Job Card Planning | /production/knitting-program | Complete | 🎨 Mockup Ready | ✅ Deployed | 32_KNITTING_PROGRAM_UI_SPECIFICATION.md
SCR-KNIT-002 | Mod 6 | Knitting & Fabric Production | Grey Fabric Inward, Outward & Live Stock | /production/grey-fabric | Complete | 🎨 Mockup Ready | ✅ Deployed | 33_GREY_FABRIC_UI_SPECIFICATION.md
SCR-PRIC-001-ADD | Mod 9 | Yarn Price Lists | Yarn Price List Add Workflow | /pricing/yarn-price-lists/new | Complete | 🎨 Mockup Ready | ✅ Deployed | 23_YARN_PRICE_LIST_ADD_WORKFLOW_SPECIFICATION.md
SCR-PRIC-001-EDIT | Mod 9 | Yarn Price Lists | Yarn Price List Edit & Revision | /pricing/yarn-price-lists/[id]/edit | Complete | 🎨 Mockup Ready | ✅ Deployed | 24_YARN_PRICE_LIST_EDIT_WORKFLOW_SPECIFICATION.md
SCR-PRIC-001-LIST | Mod 9 | Yarn Price Lists | Yarn Price List Register & Management | /pricing/yarn-price-lists | Complete | 🎨 Mockup Ready | ✅ Deployed | 25_YARN_PRICE_LIST_LIST_WORKFLOW_SPECIFICATION.md
SCR-PRIC-001-PRINT | Mod 9 | Yarn Price Lists | Yarn Price List (Rate Card) Print | /pricing/yarn-price-lists/[id]/print | Complete | 🎨 Mockup Ready | ✅ Deployed | 26_YARN_PRICE_LIST_PRINT_DOCUMENT_SPECIFICATION.md
SCR-PRIC-002 | Mod 9 | Job Work Subcontract Matrix | Job Work Subcontract Conversion Matrix | /pricing/job-work-rules | Complete | 🎨 Mockup Ready | ✅ Deployed | 37_JOB_WORK_MATRIX_UI_SPECIFICATION.md
SCR-PRCS-001 | Mod 7 | Production Process Engine | Production Process Routing & Tracking | /production/process-routing | Complete | 🎨 Mockup Ready | ✅ Deployed | 34_PROCESS_ROUTING_UI_SPECIFICATION.md
SCR-FINL-001 | Mod 8 | Financial Ledgers & Accounting | Party Financial Ledger & Reconciliation | /ledgers/party-ledger | Complete | 🎨 Mockup Ready | ✅ Deployed | 35_PARTY_FINANCIAL_LEDGER_UI_SPECIFICATION.md
SCR-FINL-002 | Mod 8 | Financial Ledgers & Accounting | General Ledger & Multi-Period Trial Balance | /ledgers/trial-balance | Complete | 🎨 Mockup Ready | ✅ Deployed | 36_TRIAL_BALANCE_UI_SPECIFICATION.md

## Backend Tickets
BACKEND MONOLITH TICKETS & MERGE VERIFICATION
Ticket ID | Module | Ticket Description | PRD Ref | Merge Status | Release Tag | Key Invariants / Models
Ticket | Module Module | Title | PRD ref | Status | Release | Notes
T9-001 | Module 9 | Unified Price Lists (Purchase, Sales, Job Work, Party & General) | §4.5 | Merged | v1.2.0 | tm_price_list, tm_price_list_item, tm_price_list_job_rule, ta_pricing_audit, seed_defaults
T9-002 | Module 9 | Job Work Subcontract Conversion Rate Engine & Multi-Tier Resolution API | §4.5 | In review | v1.2.0 | /api/v1/pricing/resolve/ (Yarn & Job Work), job-rules CRUD, 13 automated tests passed
T0-001 | Module 0 | Workspace, base models, standard JSON envelope | §1 | Merged | v1.0.0 | TimeStamped, SoftDelete, Uppercase
T0-002 | Module 0 | Tenant & Financial Year Middleware | §3 | Merged | v1.0.0 | TenantMiddleware, X-Company-ID
T1-001 | Module 1 | Custom User, Role, Privilege, SimpleJWT Auth | §2 | Merged | v1.0.0 | 18 permission modules
T1-002 | Module 1 | Dual-route aliases and CORS header support | §2 | Merged | v1.0.0 | /api/v1/auth/login direct route
T2-001 | Module 2 | Textile Masters (Parties, Yarn, Fabric, Process, Godowns) | §4.1 | Merged | v1.0.0 | UOM, Counts, Colors, Fabrics
T2-002 | Module 2 | Quality Program carton nested sizing | §4.1 | Merged | v1.0.0 | Box ratios, nested serializers
T2-003 | Module 2 | Tax Master & GST Engine (0%, 5%, 12%, 18%, 28%, HSN/SAC) | §4.1 | Merged | v1.1.0 | mx_tax, TaxEngine, seed_defaults
T3-001 | Module 3 | Yarn Purchase Orders with split delivery schedules | §4.2 | Merged | v1.0.0 | Draft, auto FY resolution
T3-002 | Module 3 | PO Authorization locking and soft-delete safeguards | §4.2 | Merged | v1.0.0 | Prevents delete of active POs
T3-003 | Module 3 | Yarn PO live balance database view scoping | §4.2 | Merged | v1.0.0 | Scoped to active company POs
T3-004 | Module 3 | Company-Configurable Multi-Type Yarn POs (Melange, Blended, Wound, etc.) | §4.2 | Merged | v1.1.0 | tc_company_yarn_type, dynamic conditional validation
T4-001 | Module 4 | Live Godown Stock Ledger (Bags & Weight tracking) | §4.3 | Merged | v1.0.0 | tm_yarn_stock atomic locks
T4-002 | Module 4 | Inward GRN with Multi-Type Yarn Specs, GST Tax & PO deduction | §4.3 | Merged | v1.1.0 | child_yarn_inward_table, technical specs, TaxEngine
T4-003 | Module 4 | Delivery Challan Outward with bag non-negative check | §4.3 | Merged | v1.0.0 | Prevents bag underflow
T4-004 | Module 4 | Atomic cancellation and stock rollback | §4.3 | Merged | v1.0.0 | cancel_inward, cancel_outward
T5-001 | Module 5 | Commercial Sales Tax Invoices & Stock Deductions | §4.4 | Merged | v1.1.0 | GST taxes (CGST/SGST/IGST), child_yarn_sales
T5-002 | Module 5 | Customer Sales Returns with GST Tax & Stock Re-crediting | §4.4 | Merged | v1.1.0 | Re-credits physical stock, GST TaxEngine
T5-003 | Module 5 | Sales and Sales Return atomic cancellation workflows | §4.4 | Merged | v1.0.0 | cancel_sales, cancel_sales_return
T6-001 | Module 6 | Knitting Program (Job Card) planning & requirement engine | §4.3 | Merged | v1.1.0 | tm_knitting_program, loss %
T6-002 | Module 6 | Live Grey Fabric Stock Ledger (Rolls & Kg tracking) | §4.3 | Merged | v1.1.0 | tm_grey_fabric_stock locks
T6-003 | Module 6 | Grey Fabric Inward GRN with process loss & job charges | §4.3 | Merged | v1.1.0 | tm_grey_fabric_inward
T6-004 | Module 6 | Grey Fabric Outward DC for Dyeing & Knitter Return | §4.3 | Merged | v1.1.0 | tm_grey_fabric_outward
T6-005 | Module 6 | Grey Fabric PO for direct trader procurement | §4.3 | Merged | v1.1.0 | tm_grey_po
T6-006 | Module 6 | Grey Fabric Commercial Sales & Customer Sales Returns | §4.3 | Merged | v1.1.0 | tm_grey_fabric_sales, returns, live stock deduction
T7-001 | Module 7 | Unified Production Process Engine (Stages, Programs, Routing) | §4.5 | Merged | v1.1.0 | mx_process_stage, tm_process_program, dynamic routing
T8-001 | Module 8 | Dual Stock & Currency Ledger Engine (In/Out, Dr/Cr) | §4.6 | Merged | v1.1.0 | tl_stock_movement, tm_stage_stock, tl_voucher, tl_voucher_line
T8-002 | Module 8 | Party Financial Ledger Maintenance & Payment Workflows | §4.6 | Merged | v1.1.0 | Opening balance, date range filter, payment/receipt recording, auto-posting from Sales & GRN
T8-003 | Module 8 | Transaction Against in Party Ledger & Party Filtering in Stock Ledger | §4.6 | Merged | v1.1.0 | StockMovementFilterSet (party, party_id, date), party-summary endpoint, transaction_against tracking